## Overview
SYNTRA SMART
SYNTRA TV — Technical Project Plan
Execution plan derived from the SYNTRA TV PRD v1.0 ¦ Prepared for SYNTRA SMART
Project Snapshot
Total backlog items | 86
Total story points | 503
Epics | 18
Planned sprints (2 wks each) | 25
Est. duration to Beta (weeks) | 50
% Complete | 0%
Story Points by Epic |  |  | Items by Priority
Epic | Items | Points | Priority | Items
Discovery & Architecture | 6 | 31 | P0 - Critical | 39
Core Backend & Infrastructure | 6 | 26 | P1 - High | 32
Authentication & Security | 8 | 42 | P2 - Medium | 15
Content Provider Integration | 4 | 29 | P3 - Low | 0
Normalization Layer | 3 | 18
Streaming & Player | 5 | 26
Live TV & EPG | 4 | 24 | Status Breakdown
VOD — Movies & Series | 3 | 18 | Status | Items
Platform Apps — Mobile, Web, Tablet | 7 | 42 | Not Started | 86
Platform Apps — Android TV & Google TV | 4 | 31 | In Progress | 0
User Accounts & Profiles | 4 | 18 | Done | 0
Search & AI Recommendations | 5 | 39 | Blocked | 0
Smart Home Integration | 4 | 26
Notifications | 2 | 8
Subscription & Payments | 5 | 31
Admin Dashboard | 6 | 39
Beta, QA & Performance | 6 | 39
Launch & Post-Launch Roadmap | 4 | 16
How to use this workbook
- Roadmap & Milestones — phase-by-phase timeline with target durations and exit criteria.
- Epics — the 18 work streams derived from the PRD, each mapped to a target phase.
- Backlog — the sprint-level task list. Update the Status column as work progresses; the Overview totals recalculate automatically.
- All estimates are in story points (Fibonacci: 1, 2, 3, 5, 8, 13) and are planning-level — recalibrate after Sprint 2 based on actual velocity.

## Roadmap & Milestones
SYNTRA SMART
Roadmap & Milestones
Phase-based delivery plan — durations are planning estimates for a mid-sized team
Phase | Focus | Duration (wks) | Start Wk | End Wk | Key Exit Criteria
Phase 0 — Discovery & Architecture | Requirements sign-off, system design, provider API contracts, environment setup | 4 | 1 | 4 | All architecture diagrams approved; dev/staging environments live; CI skeleton running
Phase 1 — Core Backend & Infrastructure | NestJS services, PostgreSQL schema, Redis cache, JWT/OAuth, Docker/K8s baseline | 8 | 5 | 12 | Auth, user, and catalog services deployed to staging with automated tests
Phase 2 — Platform Apps (MVP) | Flutter apps for Mobile, Web, Tablet with core navigation, profiles, and player | 10 | 13 | 22 | MVP apps installable/browsable with mock catalog and working playback
Phase 3 — Content Provider Integration & Streaming | Provider layer, normalization layer, HLS/DASH pipeline, Live TV, VOD catalogs | 8 | 23 | 30 | At least one licensed IPTV and one VOD provider fully live end-to-end
Phase 4 — TV Platforms, AI & Smart Home | Android TV / Google TV apps, recommendations, smart home bridge, subscriptions | 8 | 31 | 38 | TV apps feature-complete; AI recommendations live; smart home controls functional
Phase 5 — Admin Dashboard & Security Hardening | Full admin console, RBAC, DRM readiness, pen-test remediation | 6 | 39 | 44 | Admin dashboard covers all management modules; security audit passed
Phase 6 — Beta & QA | Closed beta across all platforms, performance tuning, bug triage | 6 | 45 | 50 | App launch < 2s and streaming startup < 3s targets met; crash-free rate > 99.5%
Phase 7 — Launch | Store submissions, CDN cutover, monitoring, go-live | 2 | 51 | 52 | Public availability on Android TV, Google TV, Android, iOS, Web, Tablet
Phase 8 — Post-Launch Roadmap | Music, Podcasts, Games, Fitness, Education, Family Dashboard, video calls | Ongoing | — | — | Prioritized per the Future Roadmap backlog, scoped quarterly

## Epics
SYNTRA SMART
Epics
18 work streams mapped from the PRD, each owned end-to-end by a squad
Epic | Description | Primary Phase | Priority
Discovery & Architecture | System design, API contracts, provider onboarding spec, environment setup | Phase 0 | P0 - Critical
Core Backend & Infrastructure | NestJS services, PostgreSQL schema, Redis cache, Docker/K8s, CI/CD | Phase 1 | P0 - Critical
Authentication & Security | JWT, OAuth, biometric login, device authorization, RBAC, encryption | Phase 1 | P0 - Critical
Content Provider Integration | Provider layer, REST connectors, playlist & EPG ingestion, auto-sync | Phase 3 | P0 - Critical
Normalization Layer | Unified schema mapping across providers, de-duplication, error handling | Phase 3 | P0 - Critical
Streaming & Player | HLS/DASH via FFmpeg, adaptive bitrate, multi-audio/subtitle, casting, PiP | Phase 3 | P0 - Critical
Live TV & EPG | Channel categories, program guide, catch-up TV, time-shift, channel search | Phase 3 | P1 - High
VOD — Movies & Series | Catalog browsing, seasons/episodes, auto-next, skip intro, resume | Phase 3 | P1 - High
Platform Apps — Mobile, Web, Tablet | Flutter clients for Android, iPhone, Web, Tablet | Phase 2 | P0 - Critical
Platform Apps — Android TV & Google TV | Flutter TV clients, remote-first navigation, D-pad focus system | Phase 4 | P0 - Critical
User Accounts & Profiles | Multi-profile, kids profile, PIN, favorites, watch history, parental controls | Phase 2 | P1 - High
Search & AI Recommendations | Global search, voice search, AI search, personalization, watch prediction | Phase 4 | P1 - High
Smart Home Integration | Lights, AC, curtains, locks, cameras, doorbell, scenes, energy monitoring | Phase 4 | P1 - High
Notifications | New content, smart home & camera alerts, system updates, push infra | Phase 4 | P2 - Medium
Subscription & Payments | Plans, billing cycles, coupons, trials, Apple/Google Pay, mada, STC Pay, Stripe | Phase 4 | P0 - Critical
Admin Dashboard | User/subscription/content/banner management, analytics, revenue, API keys | Phase 5 | P1 - High
Beta, QA & Performance | Closed beta, load testing, crash triage, performance targets, low-bandwidth mode | Phase 6 | P0 - Critical
Launch & Post-Launch Roadmap | Store submissions, CDN cutover, go-live, and Phase 8 roadmap intake | Phase 7 | P1 - High

## Backlog
SYNTRA SMART
Sprint Backlog
Sprint length: 2 weeks ¦ Update Status as work progresses — Overview totals recalculate automatically
ID | Epic | Task | Platform / Area | Priority | Points | Sprint | Phase | Status | Notes
TV-001 | Discovery & Architecture | Define system architecture (provider -> normalization -> DB -> cache -> API -> apps) | Cross-platform | P0 - Critical | 8 | 1 | Phase 0 | Not Started
TV-002 | Discovery & Architecture | Author provider onboarding spec (REST, auth, playlist, EPG, HLS URLs) | Backend | P0 - Critical | 5 | 1 | Phase 0 | Not Started
TV-003 | Discovery & Architecture | Define PostgreSQL schema (catalog, users, subscriptions, entitlements) | Backend | P0 - Critical | 5 | 1 | Phase 0 | Not Started
TV-004 | Discovery & Architecture | Stand up dev/staging environments (Docker, Kubernetes namespace, CDN) | DevOps | P0 - Critical | 5 | 2 | Phase 0 | Not Started
TV-005 | Discovery & Architecture | Define brand design system in Figma (dark theme, navy/green, components) | Design | P1 - High | 5 | 2 | Phase 0 | Not Started
TV-006 | Discovery & Architecture | Draft REST API contract (OpenAPI) for application layer | Backend | P0 - Critical | 3 | 2 | Phase 0 | Not Started
TV-007 | Core Backend & Infrastructure | Scaffold NestJS monorepo with modular service boundaries | Backend | P0 - Critical | 5 | 3 | Phase 1 | Not Started
TV-008 | Core Backend & Infrastructure | Implement PostgreSQL migrations and seed data | Backend | P0 - Critical | 5 | 3 | Phase 1 | Not Started
TV-009 | Core Backend & Infrastructure | Stand up Redis cache layer for playlists/EPG/session data | Backend | P0 - Critical | 3 | 3 | Phase 1 | Not Started
TV-010 | Core Backend & Infrastructure | Implement S3-compatible storage integration for media assets | Backend | P1 - High | 3 | 4 | Phase 1 | Not Started
TV-011 | Core Backend & Infrastructure | Set up CI/CD pipeline (build, test, deploy to staging) | DevOps | P0 - Critical | 5 | 4 | Phase 1 | Not Started
TV-012 | Core Backend & Infrastructure | Containerize services and write Kubernetes manifests | DevOps | P0 - Critical | 5 | 4 | Phase 1 | Not Started
TV-013 | Authentication & Security | Implement JWT auth with refresh tokens | Backend | P0 - Critical | 5 | 5 | Phase 1 | Not Started
TV-014 | Authentication & Security | Add OAuth (Google/Apple) login | Backend | P0 - Critical | 5 | 5 | Phase 1 | Not Started
TV-015 | Authentication & Security | Implement biometric login on mobile clients | Mobile | P1 - High | 3 | 5 | Phase 1 | Not Started
TV-016 | Authentication & Security | Device authorization and session management | Backend | P0 - Critical | 5 | 6 | Phase 1 | Not Started
TV-017 | Authentication & Security | Role-based access control for admin & API | Backend | P0 - Critical | 5 | 6 | Phase 1 | Not Started
TV-018 | Authentication & Security | Enforce HTTPS, API encryption, and secrets management | DevOps | P0 - Critical | 3 | 6 | Phase 1 | Not Started
TV-019 | Platform Apps — Mobile, Web, Tablet | Flutter app shell: navigation, theming, routing (Mobile/Web/Tablet) | Mobile/Web | P0 - Critical | 8 | 6 | Phase 2 | Not Started
TV-020 | Platform Apps — Mobile, Web, Tablet | Build Home screen (hero banner + content rails) | Mobile/Web | P0 - Critical | 8 | 7 | Phase 2 | Not Started
TV-021 | Platform Apps — Mobile, Web, Tablet | Build video player screen (adaptive playback, PiP, casting) | Mobile/Web | P0 - Critical | 8 | 7 | Phase 2 | Not Started
TV-022 | Platform Apps — Mobile, Web, Tablet | Implement responsive tablet layout | Tablet | P1 - High | 5 | 8 | Phase 2 | Not Started
TV-023 | Platform Apps — Mobile, Web, Tablet | Implement Chromecast casting support | Mobile | P1 - High | 5 | 8 | Phase 2 | Not Started
TV-024 | User Accounts & Profiles | Multi-profile creation and switching | Cross-platform | P1 - High | 5 | 8 | Phase 2 | Not Started
TV-025 | User Accounts & Profiles | Kids profile with curated catalog and PIN gate | Cross-platform | P1 - High | 5 | 9 | Phase 2 | Not Started
TV-026 | User Accounts & Profiles | Favorites, watch history, and continue-watching sync | Backend | P1 - High | 5 | 9 | Phase 2 | Not Started
TV-027 | User Accounts & Profiles | Parental controls with content-rating gates | Cross-platform | P1 - High | 3 | 9 | Phase 2 | Not Started
TV-028 | Platform Apps — Mobile, Web, Tablet | Global search UI (movies, series, channels, genres, actors) | Cross-platform | P1 - High | 5 | 10 | Phase 2 | Not Started
TV-029 | Platform Apps — Mobile, Web, Tablet | Settings screen (account, playback, notifications, device mgmt) | Cross-platform | P2 - Medium | 3 | 10 | Phase 2 | Not Started
TV-030 | Content Provider Integration | Build generic provider adapter interface (auth, REST, playlist, EPG) | Backend | P0 - Critical | 8 | 10 | Phase 3 | Not Started
TV-031 | Content Provider Integration | Integrate first licensed IPTV provider end-to-end | Backend | P0 - Critical | 8 | 11 | Phase 3 | Not Started
TV-032 | Content Provider Integration | Integrate first licensed VOD provider end-to-end | Backend | P0 - Critical | 8 | 11 | Phase 3 | Not Started
TV-033 | Content Provider Integration | Scheduled auto-sync jobs with error handling & retries | Backend | P1 - High | 5 | 12 | Phase 3 | Not Started
TV-034 | Normalization Layer | Design unified content schema (movies, series, live, categories) | Backend | P0 - Critical | 5 | 10 | Phase 3 | Not Started
TV-035 | Normalization Layer | Build normalization pipeline with de-duplication | Backend | P0 - Critical | 8 | 11 | Phase 3 | Not Started
TV-036 | Normalization Layer | Cache normalized catalog in Redis with invalidation strategy | Backend | P1 - High | 5 | 12 | Phase 3 | Not Started
TV-037 | Streaming & Player | HLS packaging pipeline via FFmpeg | Backend | P0 - Critical | 8 | 12 | Phase 3 | Not Started
TV-038 | Streaming & Player | MPEG-DASH packaging pipeline via FFmpeg | Backend | P1 - High | 5 | 12 | Phase 3 | Not Started
TV-039 | Streaming & Player | Adaptive bitrate switching in player | Cross-platform | P0 - Critical | 5 | 13 | Phase 3 | Not Started
TV-040 | Streaming & Player | Multiple audio tracks and subtitle tracks in player | Cross-platform | P1 - High | 5 | 13 | Phase 3 | Not Started
TV-041 | Streaming & Player | Playback speed control and manual quality selection | Cross-platform | P2 - Medium | 3 | 13 | Phase 3 | Not Started
TV-042 | Live TV & EPG | Channel categories and favorites | Cross-platform | P1 - High | 5 | 13 | Phase 3 | Not Started
TV-043 | Live TV & EPG | Electronic Program Guide (EPG) UI | Cross-platform | P1 - High | 8 | 14 | Phase 3 | Not Started
TV-044 | Live TV & EPG | Catch-up TV and time-shift playback | Backend | P1 - High | 8 | 14 | Phase 3 | Not Started
TV-045 | Live TV & EPG | Channel search | Cross-platform | P2 - Medium | 3 | 14 | Phase 3 | Not Started
TV-046 | VOD — Movies & Series | Movies catalog: trending, latest, popular, continue watching | Cross-platform | P1 - High | 5 | 13 | Phase 3 | Not Started
TV-047 | VOD — Movies & Series | Series catalog with full season/episode support | Cross-platform | P1 - High | 8 | 14 | Phase 3 | Not Started
TV-048 | VOD — Movies & Series | Auto-play next episode and skip intro | Cross-platform | P2 - Medium | 5 | 14 | Phase 3 | Not Started
TV-049 | Platform Apps — Android TV & Google TV | Flutter TV app shell with D-pad focus navigation | TV | P0 - Critical | 8 | 14 | Phase 4 | Not Started
TV-050 | Platform Apps — Android TV & Google TV | Port Home, Live TV, Movies, Series screens to 10-foot UI | TV | P0 - Critical | 13 | 15 | Phase 4 | Not Started
TV-051 | Platform Apps — Android TV & Google TV | TV-optimized player controls and quick settings | TV | P1 - High | 5 | 15 | Phase 4 | Not Started
TV-052 | Platform Apps — Android TV & Google TV | Google TV channel row & deep-link integration | TV | P1 - High | 5 | 16 | Phase 4 | Not Started
TV-053 | Search & AI Recommendations | Personalized recommendation engine (collaborative + content-based) | Backend | P1 - High | 13 | 15 | Phase 4 | Not Started
TV-054 | Search & AI Recommendations | AI-assisted natural-language search | Backend | P1 - High | 8 | 16 | Phase 4 | Not Started
TV-055 | Search & AI Recommendations | Voice search integration | Cross-platform | P2 - Medium | 5 | 16 | Phase 4 | Not Started
TV-056 | Search & AI Recommendations | Watch prediction and content classification models | Backend | P2 - Medium | 8 | 17 | Phase 4 | Not Started
TV-057 | Search & AI Recommendations | User behavior analytics pipeline | Backend | P2 - Medium | 5 | 17 | Phase 4 | Not Started
TV-058 | Smart Home Integration | Smart home bridge service (lights, AC, curtains, doors, locks) | Backend | P1 - High | 8 | 16 | Phase 4 | Not Started
TV-059 | Smart Home Integration | Scenes and energy monitoring dashboard widgets | Cross-platform | P2 - Medium | 5 | 17 | Phase 4 | Not Started
TV-060 | Smart Home Integration | Live camera viewing, door camera, and recordings | Cross-platform | P1 - High | 8 | 17 | Phase 4 | Not Started
TV-061 | Smart Home Integration | Voice assistant integration for smart home controls | Cross-platform | P2 - Medium | 5 | 18 | Phase 4 | Not Started
TV-062 | Notifications | Push notification infrastructure (new content, system updates) | Backend | P2 - Medium | 5 | 17 | Phase 4 | Not Started
TV-063 | Notifications | Motion & camera alert notifications | Backend | P2 - Medium | 3 | 18 | Phase 4 | Not Started
TV-064 | Subscription & Payments | Plan management: Free, Premium, Family, Business | Backend | P0 - Critical | 8 | 16 | Phase 4 | Not Started
TV-065 | Subscription & Payments | Monthly/yearly billing cycles, coupons, and free trial | Backend | P0 - Critical | 5 | 17 | Phase 4 | Not Started
TV-066 | Subscription & Payments | Stripe, Visa/Mastercard payment integration | Backend | P0 - Critical | 8 | 17 | Phase 4 | Not Started
TV-067 | Subscription & Payments | Apple Pay and Google Pay integration | Mobile | P0 - Critical | 5 | 18 | Phase 4 | Not Started
TV-068 | Subscription & Payments | mada and STC Pay integration (KSA) | Backend | P1 - High | 5 | 18 | Phase 4 | Not Started
TV-069 | Admin Dashboard | Admin shell, auth, and role-based navigation | Admin | P1 - High | 5 | 18 | Phase 5 | Not Started
TV-070 | Admin Dashboard | User and subscription management modules | Admin | P1 - High | 8 | 19 | Phase 5 | Not Started
TV-071 | Admin Dashboard | Channel, movie, and series management modules | Admin | P1 - High | 8 | 19 | Phase 5 | Not Started
TV-072 | Admin Dashboard | Banner and category management | Admin | P2 - Medium | 5 | 20 | Phase 5 | Not Started
TV-073 | Admin Dashboard | Analytics and revenue reporting | Admin | P1 - High | 8 | 20 | Phase 5 | Not Started
TV-074 | Admin Dashboard | Coupons, notifications console, and API key management | Admin | P2 - Medium | 5 | 20 | Phase 5 | Not Started
TV-075 | Authentication & Security | DRM-readiness integration and content protection review | Backend | P0 - Critical | 8 | 19 | Phase 5 | Not Started
TV-076 | Authentication & Security | External penetration test and remediation | DevOps | P0 - Critical | 8 | 21 | Phase 5 | Not Started
TV-077 | Beta, QA & Performance | Closed beta rollout across all six launch platforms | Cross-platform | P0 - Critical | 8 | 21 | Phase 6 | Not Started
TV-078 | Beta, QA & Performance | Performance tuning: app launch < 2s, stream startup < 3s | Cross-platform | P0 - Critical | 8 | 22 | Phase 6 | Not Started
TV-079 | Beta, QA & Performance | Offline cache and low-bandwidth mode | Cross-platform | P1 - High | 5 | 22 | Phase 6 | Not Started
TV-080 | Beta, QA & Performance | 4K playback validation across supported devices | Cross-platform | P1 - High | 5 | 23 | Phase 6 | Not Started
TV-081 | Beta, QA & Performance | Crash triage and stability hardening | Cross-platform | P0 - Critical | 8 | 23 | Phase 6 | Not Started
TV-082 | Beta, QA & Performance | Accessibility and localization QA pass | Cross-platform | P2 - Medium | 5 | 24 | Phase 6 | Not Started
TV-083 | Launch & Post-Launch Roadmap | App store submissions (Play Store, App Store, TV stores) | Cross-platform | P0 - Critical | 5 | 25 | Phase 7 | Not Started
TV-084 | Launch & Post-Launch Roadmap | CDN cutover and production monitoring/alerting | DevOps | P0 - Critical | 5 | 25 | Phase 7 | Not Started
TV-085 | Launch & Post-Launch Roadmap | Go-live and launch-day support rotation | Cross-platform | P0 - Critical | 3 | 25 | Phase 7 | Not Started
TV-086 | Launch & Post-Launch Roadmap | Scope Phase 8 roadmap: Music, Podcasts, Games, Fitness, Education | Product | P2 - Medium | 3 | 25 | Phase 8 | Not Started